## SUMMARY
INDIRA GANDHI INSTITUTE OF RESEARCH UP-GRADATION OF INFRASTRUCTURE FACILITIES
SUMMARY FOR REPAIRING & WATERPROOFING WORK FOR RESIDENTIAL BUILDING B', D' & E' (PHASE-3), IN THE CAMPUS.
SR NO. | ITEM | AMOUNT
1 | REPAIRING & WATERPROOFING WORK FOR RESIDENTIAL BUILDING B', D' & E'
Existing Work Amount (Part A)
New Work Amount (Part B)
Total Amount
Add:- SGST @ 9%
Add:- CGST @ 9%
Grand Total Amount Rs.
Say,

## BOQ CIVIL
UPGRADATION OF INFRASTRUCTURAL FACILITIES IN IGIDR, GOREGAON.
QUOTATION FOR REPAIRING & WATERPROOFING WORK FOR RESIDENTIAL BUILDING B', D' & E' STRUCTURES IN THE CAMPUS.
Quoted Amount
Sr. No. | Item Description | Quantity | Unit | final excess saving qty | up to 7th RA Bill Qty | Rate | Amount
A. | Existing Work Amount
1 | Bamboo Scaffolding :- Providing & erecting Double stage bamboo scaffolding in true vertical position with necessary staging at regular intervals as per site requirement with all necessary accessories. The scaffolding to be jointed with coir strings etc. complete. | 312 | Smt. | 15992.27 | 12465.33
2 | Breaking of existing plaster:-Removing / breaking carefully the existing plaster including the tiles on the surface wherever required, of any thickness, as directed,, disposing off the debris, cleaning ,etc complete. | 72 | Smt. | 9807.65 | 6121.1
3 | Sand Face Plaster :- Providing Applying 35mm Sand face cement plaster in two coats, using approved river sand, first coat of required thickness in C.M 1:4 with addition of approved waterproofing compound/plastisizer, finishing to line, level & plumb, etc. complete as per specifications and as directed by the consultants. Second coat 15 mm thick in C.M. 1:3, finishing, cleaning, curing etc. | 72 | Smt. | 9971.35 | 6296.32
4 | Providing Applying Dash cost along with PP Net Providing & applying 25mm thk dash coat on existing stone masonary wall surfacein cement morter 1:4 Providing & Fixing PP Net on entire surface befor plaster including curing etc complete. | 72 | Smt. | 466 | 33552
5 | PLASTIC EMULSION | 35 | Smt.
Providing & applying plastic emulsion paint on walls, columns & ceilings. The rate shall include scrapping, levelling & preparing the surface. Primer coat + (minimum) 3 coats to get evenly spread quality finish (roller finish) of approved make , quality & finish shall be provided.
6 | Providing & applying water proofing cement paint on walls of required shade after applying base coat & primer as per manufacturers specifications in proper line & level & even colour texture, without patches. | 108 | Smt.
7 | Waterproof Coating :- Providing & applying two coats of Acrylic based polymer coating made out of grey cement confirming to relevant BIS specification mixed with acrylic base polymer in proportion of 1:1 mixed with the help of mechanical stirrer. Applying the coating in zebra manner in reverse direction all as per the direction of the engineer in charge. | 108 | Smt.
8 | WATER PROOFING-upto depth of 350mm | 10 | Smt.
Providing and laying integral cement based water proofing treatment including preperation of surface as required for treatment of toilet slab etc. consisting of following operations.
Applying and grounting a slurry coat of neat cement using 2.75 kg/sqm. Of cement admixed with proprietary water proofing compound conforming to IS: 2645 over the RCC slab including cleaning the surface before treatment.
Laying cement concrete using broken bricks/brick bats 25 mm to 100 mm size with 50% of cement mortar 1:5 ( 1 cement : 5 coarse sand) admixed with proprietory water proofing compound conforming to IS :2645 to required slope and treating similarly the adjoining walls upto 300 mm height including rounding of junctions of walls and slabs.
After two days of proper curing applying a second coat of cement slurry admixed with proprietory water proofing compound conforming to IS : 2645.
Finishing the surface with 20 mm thick jointless cement mortar of mix 1:4 ( 1 cement :4 coarse sand ) admixed with proprietary water proofing compond conforming to IS : 2645 and finally finishing the surface with trowel with neat cement slurry and making of 300x300 mm square.
The whole area so finished shall be flooded with water for a minimum period of two weeks for curing and for final test. All above operations to be done in order and as directed and specified by the Engineer-in-Charge.
9 | Providing & laying China mosaic tretment with broken glazed/ ceramic tiles in proper workmanlike manner and laid to slopes including 20mm thick bedding material in CM 1:6 with cleaning the surface & leaving the surface stainfree, etc complete. | 10 | Smt.
Total Amount ( A)
Add:- SGST @ 9%
Add:- CGST @ 9%
Total Amount (A) Rs.
Total Part (A) Say,
B. | New Work Amount
1 | Bamboo Scaffolding :- Providing & erecting Double stage bamboo scaffolding in true vertical position with necessary staging at regular intervals as per site requirement with all necessary accessories. The scaffolding to be jointed with coir strings etc. complete. | 312 | Smt. | 15992.27 | 12465.33
2 | Breaking of existing plaster:-Removing / breaking carefully the existing plaster including the tiles on the surface wherever required, of any thickness, as directed,, disposing off the debris, cleaning ,etc complete. | 68 | Smt. | 9807.65 | 6121.1
3 | Sand Face Plaster :- Providing Applying 35mm Sand face cement plaster in two coats, using approved river sand, first coat of required thickness in C.M 1:4 with addition of approved waterproofing compound/plastisizer, finishing to line, level & plumb, etc. complete as per specifications and as directed by the consultants. Second coat 15 mm thick in C.M. 1:3, finishing, cleaning, curing etc. | 68 | Smt. | 9971.35 | 6296.32
4 | Providing Applying Dash cost along with PP Net Providing & applying 25mm thk dash coat on existing stone masonary wall surfacein cement morter 1:4 Providing & Fixing PP Net on entire surface befor plaster including curing etc complete. | 68 | Smt. | 466 | 31688
5 | PLASTERING (Internal Additional Plastering) | 8 | Smt. | 9971.35 | 6296.32
Providing & applying 15mm cement sand plaster of 1:4 proportion to existing brick / RCC walls & ceilings in single coat of avg. ¾” thk. Finished rough to receive plaster of paris levelling coat. The rate shall include necessary scaffolding, curing etc. Complete.
6 | Providing & applying water proofing cement paint on walls of required shade after applying base coat & primer as per manufacturers specifications in proper line & level & even colour texture, without patches. | 97 | Smt.
7 | Waterproof Coating :- Providing & applying two coats of Acrylic based polymer coating made out of grey cement confirming to relevant BIS specification mixed with acrylic base polymer in proportion of 1:1 mixed with the help of mechanical stirrer. Applying the coating in zebra manner in reverse direction all as per the direction of the engineer in charge. | 97 | Smt.
8 | FLOORING
a. | CERAMIC TILE FLOORING | 4 | Smt.
Providing and fixing 12” x 12” Ceramic Tiles of approved make, quality & shade and pattern as shown in the drg. In CM 1:4 in proper line and level. Rate shall be inclusive of providing and laying necessary backing material and joint filling compound of the same shade of the tiles
b. | VITRIFIED TILES FLOORING | 4 | Smt.
Providing and fixing 24” X 24” VITRIFIED Tiles of approved make, 1st quality & shade and pattern as shown in the drg. In CM 1:4 in proper line and level and also using 3mm approved spacers for maintaining the grid lines. Rate shall be inclusive of providing and laying necessary backing material and joint filling compound of the same shade of the tiles.Approved mke shall be Johnson/Nitco/Kajaria or equivalent.
9 | SKIRTING AND DADO
a. | CERAMIC TILE DADO | 10 | Smt.
Providing and fixing approved shade of ceramic tiles as per pattern for dado from FFL using CM 1:4 in proper line and level as directed by the Architect as shown in the drawings. The rate shall include necessary backing material, water proofing and joint filling compound of the same shade as that of the ceramic tiles. All sanitary fittings shall be located on the joints or junctions of the tiles..Rate inclusive of Highlighter Border Tiles.
b. | VITRIFIED TILE SKIRTING | 30 | Rmt.
4" HIGH
10 | FALSE CEILING - GYP BOARD | 15 | Smt.
Providing and fixing ½” thk. Gypsum India board false ceiling at levels as shown in the drg. From FFL. Rate shall be inclusive of all Gypsum India components contained G.I. perimeter channels of size 0.55 thick having one flange of 20mm and another flange of 30mm and a web of 27mm alongwith perimeter of ceiling, screw fixed to brickwall/partition with the help of nylon sleeves and screws, at 610mm centres. The suspending G.I.intermediate channels of size 45mm, 0.9mm thick with two flanges of 15mm each from the soffite at 1220mm centres with ceiling angle of width 25mm x 10mm x 0.55 thick fixed to soffite with G.I. cleat and steel expansion fastners at every 610mm c/c. Ceiling sections of 0.55mm thickness having knurled web of 51.5mm and two flanges of 26mm each with lips of 10.5mm are then fixed to intermediate channel with the help of connecting clip and in direction perpendicular to the intermediate channel at 457mm centres.
The boards are to be jointed and finished so as to have a flush look which includes filling and finishing the tapered and squre edge of the boards with jointing compound & joint paper tape. Rate shall be inclusive of any vertical 12.5mm tapered edge Gypboard is then screw fixed to ceiling section with 25mm drywall screws driver or drilling machine with suitable attachment. ceiling part, spot, tube light, a. C. Grills, fire and security systems cut outs, All Sections should adhere to the manufacturers guidelines and contractor has to submit the Gypsum India certificate on using the India Gypsum sections & boards. Refer attached sheet along with drawings for details.
11 | PLASTIC EMULSION | 35 | Smt.
Providing & applying plastic emulsion paint on walls, columns & ceilings. The rate shall include scrapping, levelling & preparing the surface. Primer coat + (minimum) 3 coats to get evenly spread quality finish (roller finish) of approved make , quality & finish shall be provided.
12 | Demolishing brick work manually/ by mechanical means including stacking of servicable material & disposal of unservicable material outside institute premises as per local municipal corporation byelaws as per direction of Engineer-in-charge. | 1 | Cum.
13 | Separation crack treatment at the junction of RCC frame and RCC pardi walls/ masonary separation cracks treatment by opening the cracks into a "V" groove, clean & moisten the groove, apply priming cum bonding coat of Polymeric mortar modifier/ cement slurry of approved manufacturers in proportion 1:1 by weight with brush to grooved surface, immediately fill the groove with Polymer modified mortar, which is prepared by mixing 2 Kgs of Polymeric mortar modifier + 5 kgs of fresh cement + 15 kgs of quartz sand (graded). After 15-20 minutes level the surface with steel trowel including 48 hours curing bt sprinkling water for 2-3 days etc as per directions complete. | 144 | Rmt. | 2103.95 | 1503.95
14 | Brick work with modular bricks of class designation 75 in foundation & plinth in.Cement mortar 1:4 ( 1 cement : 4 coarse sand ) | 0.5 | Cum.
15 | Cement Grouting :- Drilling the holes with help of Mechnical drilling machine, providing & fixing PVC perforated nipples, providing & injecting Non shrink cemnetitious grout into the nipples etc. complete. | 320 | Nos. | 3470 | 3440
16 | Exposing:-Dismantling Rcc members carefully of any size/shape, as directed, without damaging other parts of the building, other parts of the building ,cutting /removing the steel bars, removing /carting away the debris, cleaning , etc. complete. Due care shall be taken so as not to damage surroundings etc. complete. | 1 | Smt. | 2325.93 | 2315.77
17 | Corrossion Treatment : Providing all materials & labour, cleaning the exposed reinforcement with wire brush & applying rust removing chemical with applying bonding coat of cement & rust passivator in the ratio of 1:1 to make it ready to receive further treatment etc. complete. | 1 | Smt. | 1304.12 | 1293.96
18 | Polymer modified mortor:-Thick to receive homogneous polymer mortor removing the loose concrete plaster etc. clean the surface with air blower & water jet. Clean he reinforcement with wire brush, apply rusticide .& clean the reinforcementt throughly Applying 2 coats of polyalk Fixoprime & cement mixture to the rinforcement bonding wat applying polymer mortar consisting of polymer cement .quartz sand (1:5:15) water in layers of average thickness 10-15mm Befor application of each layer of the polymer mortar a bonding coat will be applied etc. complete (Upto 20 mm thick) | 1 | Smt. | 1304.12 | 1293.96
19 | Demolishing RCC work manually/ by mechanical means incl stacking of steel bars & disposal of unservicable material within 50 mts lead as per directions of engineer in charge. Rate to include that for gas cutting of MS reinforcement if required as per the directions of the engineer. | 1 | Cum.
20 | Truck For Debris | 3 | Nos.
21 | Dismantling aluminium /gypsum partitions and false ceiling including disposal of unserviceable surplus maetrial outside institute premises as per local municipal corporation byelaws and stacking of serviceable material as directed by engineer. | 15 | Smt.
22 | Dismantling tile work in floors laid in cement mortar including disposing off the unserviceable material outside institute premises as per local municipal corporation byelaws for thickness of tiles 10mm to 25mm | 53 | Smt.
23 | BIRLA PUTTY | 50 | Smt.
Providing and applying 1&2 coats Birla Putty Including Scrapping Existing Old Damaged Paint Surface To Receive New Paint.
24 | WATER PROOFING-upto depth of 350mm | 5 | Smt.
Providing and laying integral cement based water proofing treatment including preperation of surface as required for treatment of toilet slab etc. consisting of following operations.
Applying and grounting a slurry coat of neat cement using 2.75 kg/sqm. Of cement admixed with proprietary water proofing compound conforming to IS: 2645 over the RCC slab including cleaning the surface before treatment.
Laying cement concrete using broken bricks/brick bats 25 mm to 100 mm size with 50% of cement mortar 1:5 ( 1 cement : 5 coarse sand) admixed with proprietory water proofing compound conforming to IS :2645 to required slope and treating similarly the adjoining walls upto 300 mm height including rounding of junctions of walls and slabs.
After two days of proper curing applying a second coat of cement slurry admixed with proprietory water proofing compound conforming to IS : 2645.
Finishing the surface with 20 mm thick jointless cement mortar of mix 1:4 ( 1 cement :4 coarse sand ) admixed with proprietary water proofing compond conforming to IS : 2645 and finally finishing the surface with trowel with neat cement slurry and making of 300x300 mm square.
The whole area so finished shall be flooded with water for a minimum period of two weeks for curing and for final test. All above operations to be done in order and as directed and specified by the Engineer-in-Charge.
25 | Providing & laying China mosaic tretment with broken glazed/ ceramic tiles in proper workmanlike manner and laid to slopes including 20mm thick bedding material in CM 1:6 with cleaning the surface & leaving the surface stainfree, etc complete. | 5 | Smt.
26 | Providing & laying in position cement concrete of specified grade excluding the cost of centering & shuttering - All work upto plinth level | 2 | Cum.
1:2:4 ( 1 Cement : 2 coarse sand : 4 graded stone aggregate 20 mm nominal size)
Total Amount ( B)
Add:- SGST @ 9%
Add:- CGST @ 9%
Total Amount (B) Rs.
Total Part (B) Say,
Grand Total Amount (A+B)
Note:-
1) All the rates shall be included of electricity supply & Water supply required for execution of work.
2) All the Taxes shall be included all taxes (GST @18%) .